## project-overview
Project overview
Welcome to your project overview board! Here you can easily manage and track your entire construction project using a high-level overview. Learn more about this template here: https://www.youtube.com/watch?v=rz2SPVGFQ2U&feature=youtu.be
More information about this template:
Name | Address | Project manager | Overall unit progress | Status | Permit | Foundations | Drywall | Trench | Framing | Electrical | Roofing | QC | Start date | Connect to "Project details" board | link to Project details
Hi there! 👋 Click here for more information ➡️
In construction
Name | Address | Project manager | Overall unit progress | Status | Permit | Foundations | Drywall | Trench | Framing | Electrical | Roofing | QC | Start date | Connect to "Project details" board | link to Project details
Address / Unit 1 | 177 Griffin St. Los Angeles, CA 90001 |  | 52% | Started | Done | Done | Done | Done | Done | Planned | Planned | Planned | 2022-05-31 | Address / Unit 1
Address / Unit 2 | 97 Old Water St. Los Angeles, CA 90066 |  | 13% | Started | Done | Done | Done | Stuck | Delayed | Planned | Planned | Planned | 2022-06-01 | Address / Unit 2
Address / Unit 3 | 124 Glenridge Drive Spring Valley, CA 91977 |  | 26% | Started | Done | Done | Done | Working on it | Working on it | Planned | Planned | Planned | 2022-06-02 | Address / Unit 3
Address / Unit 4 | 9569 Theatre St. Oceanside, CA 92056 |  | 39% | Started | Done | Done | Done | Done | Working on it | Planned | Planned | Planned | 2022-06-03 | Address / Unit 4
2022-05-31 to 2022-06-03
Done
Name | Address | Project manager | Overall unit progress | Status | Permit | Foundations | Drywall | Trench | Framing | Electrical | Roofing | QC | Start date | Connect to "Project details" board | link to Project details
Address / Unit 6 | 9876 Fulton Lane San Jose, CA 95116 |  | 100% | Job completed | Done | Done | Done | Done | Done | Done | Done | Done | 2022-06-04 | Address / Unit 6
2022-06-04