## construction-projects
Construction Projects - High Level View
In this board, you will find all of the currently running projects our company is working on. This board does not contain done projects, or upcoming projects we didn't start working on.
Initiation
Name | Project Manager | Stage | Timeline - Start | Timeline - End | Location | Total Budget | Budget Spent | Budget Status? | Budget Gaps | Upcoming Status Meeting | Link to Project
Fairview Project |  | Business Case | 2022-06-09 | 2022-09-08 | Fairview, New Jersey, USA | 550000 | 250550 | Within Budget | 299450 | 2022-08-21 | Fairview Project - http://www.
Forest Hill Project |  | Feasibility Study | 2022-04-09 | 2022-09-08 | Forest Hills, Queens, NY, USA | 800000 | 850000 | Over Budget | -50000 | 2022-08-22 | Forest Hill Project - http://www
James Jr Condominium |  | Done | 2022-02-08 | 2023-02-08 | James Jr Ave, Danielson, CT, USA | 1000000 | 395000 | Within Budget | 605000 | 2022-08-25 | James Jr Condominium - http://www
|  |  | 2022-02-08 | 2023-02-08 |  | 2350000 | 1495550 | 0 | 854450 | 2022-08-21 to 2022-08-25
Design and Planning
Name | Project Manager | Stage | Timeline - Start | Timeline - End | Location | Total Budget | Budget Spent | Budget Status? | Budget Gaps | Upcoming Status Meeting | Link to Project
Kimmel High School |  | Phase Review | 2022-07-09 | 2022-10-07 | 244 Rutherford Drive, Toronto | 700000 | 220000 | Within Budget | 480000 | 2022-08-19 | Kimmel High School - http://www
45 New Hampshire Road |  | Design | 2022-08-17 | 2022-08-30 | 45 New Hemphire Road, Toronto | 78000 | 75000 | Within Budget | 3000 | 2022-08-22 | 45 New Hampshire Road - http://ww
Bathurst Street Commercial Project |  | Cost, Schedule, Timeline | 2022-03-13 | 2022-12-12 | 4779 Bathurst Street, Toronto, ON, Canada | 2000000 | 1300000 | Within Budget | 700000 | 2022-08-25 | Bathurst Street Commercial Project - http://ww
|  |  | 2022-03-13 | 2022-12-12 |  | 2778000 | 1595000 | 0 | 1183000 | 2022-08-19 to 2022-08-25
Bidding and Procurement
Name | Project Manager | Stage | Timeline - Start | Timeline - End | Location | Total Budget | Budget Spent | Budget Status? | Budget Gaps | Upcoming Status Meeting | Link to Project
Unit #7880 Cunningham Street |  | Engineering | 2022-07-17 | 2022-11-22 | Cunningham Avenue, Toronto, ON, Canada | 45000 | 13000 | Within Budget | 32000 | 2022-09-09 | Unit #7880 Cunningham Street - http://ww
|  |  | 2022-07-17 | 2022-11-22 |  | 45000 | 13000 | 0 | 32000 | 2022-09-09
Execution and Construction
Name | Project Manager | Stage | Timeline - Start | Timeline - End | Location | Total Budget | Budget Spent | Budget Status? | Budget Gaps | Upcoming Status Meeting | Link to Project
Westmount Boulevard Project |  | Procurement | 2022-07-24 | 2022-10-24 | Westmount Boulevard, Thornhill, ON, Canada | 3000000 | 70000 | Within Budget | 2930000 | 2022-09-10 | Westmount Boulevard Project - http://ww
Greenlawn Project |  | Construction | 2022-08-09 | 2022-12-08 | Green Lane, Thornhill, ON, Canada | 1000000 | 580000 | Within Budget | 420000 | 2022-09-11 | Greenlawn Project - http://ww
|  |  | 2022-07-24 | 2022-12-08 |  | 4000000 | 650000 | 0 | 3350000 | 2022-09-10 to 2022-09-11
Close-out
Name | Project Manager | Stage | Timeline - Start | Timeline - End | Location | Total Budget | Budget Spent | Budget Status? | Budget Gaps | Upcoming Status Meeting | Link to Project
Unit #466 Yonge Street |  | Performance and Monitoring | 2022-05-09 | 2022-09-08 | Yonge Street, Newmarket, ON, Canada | 8000 | 9000 | Over Budget | -1000 | 2022-08-18 | Unit #466 Yonge Street - http://ww
King St. Project |  | Pass to owner | 2022-05-09 | 2022-09-27 | 8576 King Street, Toronto, ON, Canada | 7500 | 7500 | Within Budget | 0 | 2022-08-25 | King St. Project - http://ww
Washington Court Project |  | Termination Provisions | 2022-08-03 | 2022-08-21 | Washington Court House, OH, USA | 150000 | 152000 | Over Budget | -2000 | 2022-08-20 | Washington Court Project - http://ww
Thornhill Court Project |  | Closing Study | 2022-05-09 | 2022-08-24 | Thornhill, Vaughan, ON, Canada | 1000000 | 950000 | Within Budget | 50000 | 2022-08-20 | Thornhill Court Project - https://michal-hanover.monday.com/boards/681019865
|  |  | 2022-05-09 | 2022-09-27 |  | 1165500 | 1118500 | 0 | 47000 | 2022-08-18 to 2022-08-25