## project-proposal
Project Proposal
The Project Proposal board will help you organize the problem definition and set up clear goals and objectives. With this board, you'll also be able to keep track of your project performance, all major milestones, and the cost-benefit analysis.
Problem definition
Name | Status | Action Type | Description / Performance measure | First year costs | Target date | Leader | Files
Problem statement | Done |  | Staten Island has relied upon a mainframe system to manage payroll and other administrative employee functions. As the number of employees grows, so does the burden placed upon headquarters to effectively manage the company’s administration at acceptable levels. |  | 2022-03-02
Organizational impact | Working on it |  | The WP Project will impact Smith Consulting in several ways. The following provides a high-level explanation of how the organization, tools, processes, and roles and responsibilities will be affected as a result of the WP Project implementation: |  | 2022-03-09
Technology Migration | Not yet started |  | In order to effectively migrate existing data from our legacy platform to the new Web-based platform, a phased approach has been developed which will result in minimal/no disruption to day to day operations, administration, and payroll activities. The following is a high-level overview of the phased approach: |  | 2022-03-09
|  |  |  | 0 | 2022-03-02 to 2022-03-09
Goals and objectives
Name | Status | Action Type | Description / Performance measure | First year costs | Target date | Leader | Files
Business Goal/Objective Description Timely and accurate reporting | Done |  | Web based tool will allow real-time and accurate reporting of all payroll and administrative metrics |  | 2022-04-14
Improve staff efficiency | Not yet started |  | Fewer HR and payroll staff required for managing these activities will improve efficiency |  | 2022-05-12
|  |  |  | 0 | 2022-04-14 to 2022-05-12
Project performance
Name | Status | Action Type | Description / Performance measure | First year costs | Target date | Leader | Files
Reporting | Done |  | The web-based system will reduce reporting discrepancies (duplicates and gaps) and require reconciliation every 6 months instead of monthly. |  | 2022-03-10
Timesheet/Admin data entry | Not yet started |  | Eliminate managers’ non-billable work by allowing employees to enter their data directly. |  | 2022-03-02
Software and System Maintenance | Not yet started |  | Decrease in cost and staff requirements as system maintenance will be reduced from once every month to once every 6 months with the new system. |  | 2022-03-09
|  |  |  | 0 | 2022-03-02 to 2022-03-10
Major project milestones
Name | Status | Action Type | Description / Performance measure | First year costs | Target date | Leader | Files
Project Charter | Working on it |  |  |  | 2022-03-23
Project Plan Review and Completion | Done |  |  |  | 2022-03-17
Project Kickoff | Done |  |  |  | 2022-03-17
|  |  |  | 0 | 2022-03-17 to 2022-03-23
Cost-benefit Analysis
Name | Status | Action Type | Description / Performance measure | First year costs | Target date | Leader | Files
Purchase Web-based product and licenses | Done | Cost | Initial investment for WP Project | 400000
Software installation and training | Done | Cost | Cost for IT group to install new software and for the training group to train all employees | 100000
System maintenance required every 6 months instead of monthly | Done | Savings | Less frequent use of IT resources working on non-value added tasks results in approximately $42,000 savings per year. | 42000
542000